## Sheet1
Sample Time Line for Master's Students
These are examples of time lines for extensions beginning in September 2017. Please include additional relevant milestones.
Student Name
Student Number
Program Start Date
Program Original End Date
Any Previous Extensions Approved
Month | Activity
September 2017 | Finish last experiment
October 2017 | Write up thesis
November 2017
December 2017
January 2018 | First draft ready - sent to supervisor
February 2018 | First draft sent to committee members
March 2018 | 2nd draft to supervisor and committee members
April 2018 | Departmental defence
May 2018 | Revision
June 2018 | Final revised thesis to G+PS
July 2018
Sample Time Line for Doctoral Students
Student Name
Student Number
Program Start Date
Program Original End Date
Any Previous Extensions Approved
Date of Advancement to Candidacy (Doctoral students only)
Month | Activity
September 2017 | Write up thesis -- Chapters 1, 2 & 3
October 2017 | Chapters 4, 5, 6
November 2017 | Chapters 7, 8, 9
December 2017 | Request for external examiner
January 2018 | first draft ready - sent to supervisor
February 2018 | first draft sent to committee members
March 2018 | 2nd draft to supervisor and committee members
Submit thesis to FoGS to send to external examiner
April 2018
May 2018 | Doctoral Oral Examination
June 2018 | Revision
July 2018 | Final revised thesis to G+PS